## Project Plan
Phase | Task | Description | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Notes
Phase 1 | Executive Sponsorship | Secure CEO/CISO commitment and budget approval |  |  |  | 5 |  | -
Phase 1 | Define ISMS Scope | Document business units, locations, systems in scope |  |  |  | 10 |  | 1
Phase 1 | Gap Analysis | Assess current state vs ISO 27001:2022 requirements |  |  |  | 20 |  | 2
Phase 1 | Project Planning | Create detailed implementation timeline and RACI |  |  |  | 5 |  | 3
Phase 2 | Policy Development | Create/update information security policies |  |  |  | 30 |  | 4
Phase 2 | Risk Assessment | Identify assets, threats, vulnerabilities, calculate risks |  |  |  | 25 |  | 4
Phase 2 | Statement of Applicability | Document control applicability and justifications |  |  |  | 10 |  | 6
Phase 2 | Control Implementation | Implement controls based on risk treatment plan |  |  |  | 60 |  | 7
Phase 2 | Documentation | Create procedures and work instructions |  |  |  | 40 |  | 8
Phase 2 | Training Program | Develop and deliver security awareness training |  |  |  | 20 |  | 5
Phase 3 | Internal Audit Planning | Define audit scope, select auditors, create schedule |  |  |  | 5 |  | 9
Phase 3 | Internal Audit Execution | Conduct audits, document findings |  |  |  | 10 |  | 11
Phase 3 | Corrective Actions | Address internal audit findings |  |  |  | 15 |  | 12
Phase 3 | Management Review | Conduct formal management review meeting |  |  |  | 2 |  | 13
Phase 4 | CB Selection | Select and contract certification body |  |  |  | 10 |  | 14
Phase 4 | Stage 1 Preparation | Prepare documentation package for Stage 1 |  |  |  | 10 |  | 15
Phase 4 | Stage 1 Audit | Documentation review with certification body |  |  |  | 2 |  | 16
Phase 4 | Stage 1 Remediation | Address Stage 1 findings |  |  |  | 20 |  | 17
Phase 5 | Stage 2 Preparation | Final preparation for certification audit |  |  |  | 10 |  | 18
Phase 5 | Stage 2 Audit | On-site certification audit |  |  |  | 5 |  | 19
Phase 5 | NC Remediation | Address any non-conformities |  |  |  | 15 |  | 20
Phase 5 | Certification | Receive ISO 27001 certificate |  |  |  | 5 |  | 21

## Mandatory Documentation
Clause | Document Name | Description | Status | Version | Approval Date | Approver | Location | Review Date
4.3 | ISMS Scope | Document defining ISMS boundaries and applicability
5.2 | Information Security Policy | Top-level policy signed by management
6.1.2 | Risk Assessment Methodology | Process for identifying and assessing risks
6.1.2 | Risk Assessment Results | Output of risk assessment activities
6.1.3 | Risk Treatment Plan | Plan for addressing identified risks
6.1.3 | Statement of Applicability | Controls applicability with justifications
6.2 | Information Security Objectives | Measurable security objectives
7.2 | Competence Evidence | Training records, certifications, qualifications
8.1 | Operational Planning Documents | Procedures for operational processes
9.2 | Internal Audit Program | Audit schedule and procedures
9.2 | Internal Audit Results | Audit reports and findings
9.3 | Management Review Records | Meeting minutes and decisions
10.1 | Nonconformity Records | NC documentation and corrective actions

## Statement of Applicability
Control ID | Control Name | Applicable | Justification | Implementation Status | Implementation Method | Reference Document
A.5.1 | Policies for information security
A.5.2 | Information security roles and responsibilities
A.5.3 | Segregation of duties
A.5.7 | Threat intelligence
A.5.23 | Information security for use of cloud services
A.6.3 | Information security awareness, education and training
A.8.9 | Configuration management
A.8.13 | Information backup
A.8.16 | Monitoring activities
A.8.28 | Secure coding

## Internal Audit Checklist
Clause/Control | Audit Question | Evidence Required | Finding | Evidence Reviewed | Auditor Notes
4.1 | How does the organization determine external and internal issues relevant to the ISMS? | Context analysis, SWOT, meeting minutes
4.2 | How are interested parties and their requirements identified? | Stakeholder register, requirements matrix
5.1 | How does top management demonstrate commitment to the ISMS? | Management review records, resource allocation
5.2 | Is the information security policy documented, communicated, and available? | Policy document, communication records
6.1 | How are risks and opportunities identified and addressed? | Risk register, risk assessment methodology
7.2 | How is competence ensured for personnel affecting ISMS? | Training records, job descriptions, certifications
8.1 | How are operational processes planned and controlled? | Procedures, work instructions, process documentation
9.1 | How is ISMS performance evaluated? | Metrics, KPIs, dashboards, reports
9.2 | Is the internal audit program implemented? | Audit schedule, audit reports, NC records
9.3 | Is management review conducted at planned intervals? | Meeting minutes, action items, decisions
10.1 | How are nonconformities addressed? | NC log, corrective action records, root cause analysis

## Management Review
ISO 27001 Management Review
Meeting Details
Date:
Attendees:
Chair:
Minutes By:
Required Inputs (ISO 27001 Clause 9.3)
a) Status of actions from previous management reviews | Status/Notes:
b) Changes in external and internal issues relevant to the ISMS | Status/Notes:
c) Feedback on information security performance, including: nonconformities and corrective actions, monitoring and measurement results, audit results, fulfillment of objectives | Status/Notes:
d) Feedback from interested parties | Status/Notes:
e) Results of risk assessment and status of risk treatment plan | Status/Notes:
f) Opportunities for continual improvement | Status/Notes:
Required Outputs
Decisions related to continual improvement opportunities | Decision/Action:
Decisions related to changes to the ISMS | Decision/Action:
Resource needs | Decision/Action:
Action Items
Action | Owner | Due Date | Status

## Audit Preparation
Stage 1 & Stage 2 Audit Preparation Checklist
Stage 1 Requirements
Item | Description | Ready | Location/Notes
ISMS Scope | Documented and approved ISMS scope statement
Information Security Policy | Signed, dated, communicated to all staff
Risk Assessment | Methodology documented, assessment completed
Risk Treatment Plan | Plan documented with owners and timelines
Statement of Applicability | All 93 controls addressed with justifications
Internal Audit Results | Audit completed, findings documented
Management Review | Review conducted, minutes available
Objectives and Metrics | Security objectives defined and measured
Competence Records | Training records for key personnel
Organization Chart | Showing ISMS roles and responsibilities
Stage 2 Requirements
All Stage 1 items | All items from Stage 1 still current
Stage 1 findings addressed | Evidence of closure for any Stage 1 findings
Operating records | 3+ months of ISMS operational evidence
Incident records | Incident log with response evidence
Access review records | Evidence of periodic access reviews
Backup/restore tests | Recent backup restore test results
Vulnerability assessments | Recent vulnerability scan results
Training records | Current training completion for all staff
Audit rooms | Quiet room for interviews prepared
Key personnel availability | Ensure all process owners available